## Dashboard
SSOD IMPLEMENTATION CONTROL DASHBOARD — S0 → S9
OVERALL PROGRESS |  |  | TASKS PASS |  |  | FAIL / BLOCKED |  | S9 AUTHORIZED?
8.125% |  |  | 13 |  |  | 0 |  | NO
CURRENT EXECUTION STATE
Current Stage | Stage Status | Next Gate
S0 | IN_PROGRESS | S0 governance artifacts valid + baseline commit/tag created
STAGE STATUS TABLE
Stage | Name | Status | Progress | PASS | Total |  | HARD-GATE MONITOR
S0 | Source / Protocol Lock Verification | CLOSED / PASS | 100% | 14 | 14 |  | S7 PASS Tasks | 0
S1 | Vast Runtime + Data Ingress + Storage/Backup | NOT_OPEN | 0% | 0 | 16 |  | S7 Total Tasks | 27
S2 | Shared Infrastructure | NOT_OPEN | 0% | 0 | 16 |  | S7 FAIL/BLOCKED | 0
S3 | Supervised Baseline | NOT_OPEN | 0% | 0 | 14 |  | S8 Status | NOT_OPEN
S4 | SSL Teacher–Student / EMA / Pseudo-label | NOT_OPEN | 0% | 0 | 20 |  | S9 Status | NOT_AUTHORIZED
S5 | Evaluation + Q_pseudo | NOT_OPEN | 0% | 0 | 10
S6 | Statistical Fixtures | NOT_OPEN | 0% | 0 | 16
S7 | Global Preflight | NOT_OPEN | 0% | 0 | 27
S8 | Freeze + Researcher Authorization | NOT_OPEN | 0% | 0 | 11
S9 | Official Training | NOT_AUTHORIZED | 0% | 0 | 16
S0 CURRENT EVIDENCE
Git branch | implementation/gate2 | Observed HEAD | 3635635beeff074534013eba5bd978ac34f9e1c9 | Baseline commit? | YES
Governance manifests | CREATED / VALIDATED | Schema verification | PASS | S0 closed? | YES

## Lists
Task Status | Stage Status | Priority | Owner
NOT_STARTED | NOT_OPEN | CRITICAL | Researcher
IN_PROGRESS | IN_PROGRESS | HIGH | ChatGPT Support
PASS | CLOSED / PASS | MEDIUM | Engineer Support
FAIL | BLOCKED / FAIL | LOW | Researcher + Support
BLOCKED | NOT_AUTHORIZED
NOT_APPLICABLE

## Detailed_Tasks
Stage | Task ID | Category | Task / Action | Requirement / Locked Rule | Primary Source | Priority | Status | Evidence / Artifact Path | Expected Result / Gate | Owner | Start Date | Due Date | Completed Date | Blocker / Dependency | Notes
S0 | S0.01 | Governance | Verify canonical filename: sn-article.tex | Canonical scientific source filename must be sn-article.tex. | sn-article.tex / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | PASS | Repository root | Canonical filename present | Researcher
S0 | S0.02 | Governance | Verify SHA-256: sn-article.tex | Must match locked scientific-source SHA-256. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | PASS | a5f63ff018ee28a37ad2daa3fff337daf6b30faf34d9f12c6ff5c0fa92fe5237 | Hash MATCH | Researcher
S0 | S0.03 | Governance | Verify SHA-256: IMPLEMENTATION_HANDOFF.md | Must match locked implementation handoff SHA-256. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | PASS | d70e556d45f4a54a5e0498842b4932deef7991de0d986095ec85e546dcc2d026 | Hash MATCH | Researcher
S0 | S0.04 | Governance | Verify SHA-256: ARTIFACT_AND_EVIDENCE_CONTRACT.md | Must match locked artifact contract SHA-256. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | PASS | 6f59fe4c097173fe0114763762dd191a6f3590caa57b28199b8bcf5100563639 | Hash MATCH | Researcher
S0 | S0.05 | Governance | Verify source priority hierarchy | sn-article.tex > IMPLEMENTATION_HANDOFF.md > ARTIFACT_AND_EVIDENCE_CONTRACT.md > execution tracker > code/config/runtime. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | PASS | Governance section | Priority order confirmed | Researcher
S0 | S0.06 | Git | Record current Git branch and HEAD commit | Capture branch/commit before implementation baseline. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | HIGH | PASS | git status + git log -1 --oneline | branch=implementation/gate2; pre-baseline HEAD=ba16e6a955f414bb7ae075625f9abf1d8dac3485 | Researcher |  |  |  |  | PASS in current S0 rerun: branch implementation/gate2 recorded before baseline; pre-baseline HEAD=ba16e6a955f414bb7ae075625f9abf1d8dac3485.
S0 | S0.07 | Governance | Create scientific_source_manifest.json | Record canonical source name/hash and lock state. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | PASS | artifacts/governance/scientific_source_manifest.json | Schema valid + hash correct | Researcher |  |  |  |  | Created in current S0 rerun by explicit PowerShell governance-manifest creation command; canonical values subsequently validated by separate JSON/schema/content verification.
S0 | S0.08 | Governance | Create implementation_contract_manifest.json | Record handoff name/hash and source hierarchy. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | PASS | artifacts/governance/implementation_contract_manifest.json | Schema valid + hash correct | Researcher |  |  |  |  | Created in current S0 rerun by explicit PowerShell governance-manifest creation command; canonical values subsequently validated by separate JSON/schema/content verification.
S0 | S0.09 | Governance | Create artifact_contract_manifest.json | Record artifact contract version/schema/hash. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | PASS | artifacts/governance/artifact_contract_manifest.json | Schema valid + hash correct | Researcher |  |  |  |  | Created in current S0 rerun by explicit PowerShell governance-manifest creation command; canonical values subsequently validated by separate JSON/schema/content verification.
S0 | S0.10 | Governance | Create schema_version.json | Record governance/artifact schema versions. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | MEDIUM | PASS | artifacts/governance/schema_version.json | Schema parse PASS | Researcher |  |  |  |  | Created in current S0 rerun by explicit PowerShell governance-manifest creation command; canonical values subsequently validated by separate JSON/schema/content verification.
S0 | S0.11 | Governance | Verify generated governance manifests and schema | JSON parse PASS; required fields present; canonical names/hashes/source hierarchy consistent with locked contracts. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | PASS | artifacts/governance/*.json | scientific_source_manifest.json + implementation_contract_manifest.json + artifact_contract_manifest.json + schema_version.json all validate | Researcher |  |  |  |  | Current S0 evidence: JSON parse PASS; required schema/name/hash/source-hierarchy checks all True; FAILED_COUNT=0; GOVERNANCE_VALIDATION=PASS.
S0 | S0.12 | Git | Create pre-implementation baseline commit | Commit intentional pre-code governance state; no model implementation. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | PASS | Git commit 3635635beeff074534013eba5bd978ac34f9e1c9 | Baseline commit created | Researcher |  |  |  |  | Pre-implementation baseline commit created and verified on implementation/gate2; exact 8-file scope verified; working tree/index clean after commit; canonical commit hashes matched.
S0 | S0.13 | Git | Create PRE_IMPLEMENTATION_BASELINE tag | Tag exact pre-implementation baseline for rollback. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | PASS | Git tag PRE_IMPLEMENTATION_BASELINE | Tag resolves to baseline commit | Researcher |  |  |  |  | Tag verified: PRE_IMPLEMENTATION_BASELINE -> 3635635beeff074534013eba5bd978ac34f9e1c9; tag commit equals baseline commit.
S0 | S0.14 | Gate | Close S0 | Only after governance manifests valid and baseline commit/tag exist. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | PASS | Workbook S0 closure record + Git baseline/tag + validated governance manifests | S0 = CLOSED / PASS | Researcher |  |  |  |  | S0 closure recorded only after S0.01-S0.13 evidence PASS, governance validation PASS, baseline commit verified, PRE_IMPLEMENTATION_BASELINE tag verified, and workbook post-save verification PASS.
S1 | S1.01 | Vast | Provision Vast instance | Use suitable Vast instance; active training/data must use Vast local/persistent storage. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | HIGH | NOT_STARTED | vast_environment.json | Instance accessible | Researcher
S1 | S1.02 | Runtime | Pull exact locked Docker image digest | quachthainguyen/sslxray-runtime@sha256:fab1b1ea8850527e5728de526b3d53f063355e84cb3a0d8c75e3a7890411d989. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | docker_image_identity.json | Digest MATCH | Researcher
S1 | S1.03 | Runtime | Capture observed Vast runtime | OS/kernel/Python/PyTorch/MMDet/MMCV/MMEngine/CUDA/cuDNN/GPU/driver/Docker digest. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | vast_environment.json | Required fields present | Researcher
S1 | S1.04 | Storage | Create project/data/artifact paths on Vast | Separate active data, artifacts, checkpoints and caches. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | HIGH | NOT_STARTED | storage_environment.json | Paths writable | Researcher
S1 | S1.05 | Data Ingress | Copy 4,894 JPG from Google Drive to Vast | Drive is transport/durable source only; no direct training I/O. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | dataset_transfer_manifest.json | Observed JPG count=4894 | Researcher
S1 | S1.06 | Data Integrity | Verify JPG count / missing / unexpected | Expected=4894; missing=0; unexpected=0. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | dataset_integrity_report.json | 4894/0/0 | Researcher
S1 | S1.07 | Data Integrity | Verify fixed split membership | Train/val/test=3426/734/734; membership hashes fixed. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | split_membership_audit.json | Counts + hashes MATCH | Researcher
S1 | S1.08 | Data Integrity | Verify No Finding counts and zero-GT identity | Train/val/test No Finding=350/75/75; not class 15. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | split_membership_audit.json | Counts MATCH | Researcher
S1 | S1.09 | Data Integrity | Verify L_b/U_b memberships | Budgets 1/5/10/20%; nested; U=T\L; exact sizes. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | labeled_unlabeled_membership_audit.json | All relations MATCH | Researcher
S1 | S1.10 | Data Integrity | Verify 1% subset coverage identity | 34 images; 14/14 classes; dedicated coverage repair moves=0. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | labeled_unlabeled_membership_audit.json | 34 + 14/14 | Researcher
S1 | S1.11 | Data Integrity | Verify class mapping | Exactly 14 detection classes; No Finding not category 15. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | class_mapping_audit.json | 14 classes MATCH | Researcher
S1 | S1.12 | Storage | Verify training path is Vast local/persistent | DataLoader must not resolve direct Google Drive paths. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | dataset_loader_manifest.json | direct_google_drive_io_for_training=false | Researcher
S1 | S1.13 | Backup | Configure Vast → Google Drive durable backup | Sync scientific artifacts/checkpoints to durable storage. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | storage_environment.json | Backup path writable | Researcher
S1 | S1.14 | Backup | Implement checksum verification for backup | Copy success alone is insufficient; verify hashes. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | backup_sync_manifest.json | verification_status=PASS | Researcher
S1 | S1.15 | Recovery | Test restore foundation | Rehydrate artifacts/checkpoint into clean path and verify hashes. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | storage_restore_test.json | PASS | Researcher
S1 | S1.16 | Gate | Close S1 | Runtime, data membership and backup/recovery verified. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | NOT_STARTED | S1 closure record | S1=CLOSED / PASS | Researcher
S2 | S2.01 | Dataset | Implement COCO dataset loading | Use fixed JSON memberships; no rebuild. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | dataset/DataLoader config | Samples resolve | Researcher
S2 | S2.02 | Dataset | Implement grayscale → 3 identical channels | R=G=B. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | sample evidence | Channels identical | Researcher
S2 | S2.03 | Dataset | Implement Resize(1333,800), keep_ratio=True | Preserve geometry. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | dataset_loader_manifest.json | MATCH | Researcher
S2 | S2.04 | Dataset | Implement pad_size_divisor=32 | Required preprocessing. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | dataset_loader_manifest.json | MATCH | Researcher
S2 | S2.05 | Dataset | Keep zero-GT No Finding samples | Do not filter empty GT. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | zero_gt_test.json | PASS | Researcher
S2 | S2.06 | Seed | Propagate training_seed to Python/NumPy/Torch CPU/CUDA | Observed/derived RNG behavior logged. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | seed_propagation_audit.json | PASS | Researcher
S2 | S2.07 | Seed | Implement DataLoader worker seeding | Record strategy and examples. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | dataloader_worker_seed_audit.json | PASS | Researcher
S2 | S2.08 | Seed | Implement sampler seeding | Controlled by training_seed. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | seed_propagation_audit.json | PASS | Researcher
S2 | S2.09 | Seed | Prove training_seed does not change membership | Same train/val/test and L/U hashes across seeds. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | training_seed_invariance_audit.json | PASS | Researcher
S2 | S2.10 | Training Infra | Implement actual optimizer-update counter | Count real optimizer steps, not raw iterations. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | preflight logs | PASS | Researcher
S2 | S2.11 | Logging | Implement run_manifest.json | Capture source/config/data/seed/runtime identity. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | run_manifest.json | Schema PASS | Researcher
S2 | S2.12 | Logging | Implement train.jsonl/runtime_events.jsonl | Event evidence incl AMP skip. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | sample logs | PASS | Researcher
S2 | S2.13 | Checkpoint | Implement checkpoint/resume foundation | Restore model/optimizer/scheduler/scaler/update/RNG states as supported. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | resume test | PASS | Researcher
S2 | S2.14 | Guardrail | Implement fail-fast source/config/data/seed checks | Block mismatch before training. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | guardrail tests | PASS | Researcher
S2 | S2.15 | Firewall | Implement hidden-U isolation foundation | Unlabeled object must not expose hidden annotations. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | hidden_u_gt_firewall_report.json | PASS | Researcher
S2 | S2.16 | Gate | Close S2 | Shared infra tests and seed/data/firewall behavior verified. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | NOT_STARTED | S2 closure record | S2=CLOSED / PASS | Researcher
S3 | S3.01 | R50 SUP | Implement Faster R-CNN R50-FPN SUP path | ImageNet-1K backbone pretraining; no COCO detector init. | sn-article.tex / IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | sup_r50_preflight.json | PASS | Researcher
S3 | S3.02 | Swin SUP | Implement Faster R-CNN Swin-T-FPN SUP path | ImageNet-1K backbone; native no-decay rules retained. | sn-article.tex / IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | sup_swin_preflight.json | PASS | Researcher
S3 | S3.03 | Optimizer | R50 SGD recipe | lr=.005, momentum=.9, wd=.0001. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | resolved config | MATCH | Researcher
S3 | S3.04 | Optimizer | Swin AdamW recipe | lr=.000025, betas=(.9,.999), wd=.05. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | resolved config | MATCH | Researcher
S3 | S3.05 | Numerics | Enable AMP / disable grad clipping | AMP ON; gradient clipping OFF. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | preflight logs | PASS | Researcher
S3 | S3.06 | Augmentation | Lock SUP pipeline Load→Resize→Pack | No flip/crop/rotation/mosaic/aggressive photometric. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | supervised_augmentation_manifest.json | MATCH | Researcher
S3 | S3.07 | Batch | Effective labeled batch = 4 | Microbatch/accumulation only to reach B_L_eff=4. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | training summary | MATCH | Researcher
S3 | S3.08 | Scheduler | Test 1% path = 1032 updates | Proportional scheduler structure. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | schedule_1pct_preflight.json | PASS | Researcher
S3 | S3.09 | Scheduler | Test standard path = 2064 updates | 5/10/20% path. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | schedule_2064_preflight.json | PASS | Researcher
S3 | S3.10 | Scheduler | Test 100%-SUP path = 10284 updates | Explicit evidence required. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | schedule_100pct_10284_preflight.json | PASS | Researcher
S3 | S3.11 | Validation | Validation every 172 actual updates | Not raw iterations. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | validation history | MATCH | Researcher
S3 | S3.12 | Checkpoint | Verify SUP BEST/LAST logic | BEST=argmax val bbox mAP@[.50:.95]; retain BEST+LAST. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | checkpoint evidence | PASS | Researcher
S3 | S3.13 | Resume | Verify SUP resume if enabled | Same seed and trajectory state. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | resume_equivalence_test.json | PASS | Researcher
S3 | S3.14 | Gate | Close S3 | All SUP official paths verified. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | NOT_STARTED | S3 closure record | S3=CLOSED / PASS | Researcher
S4 | S4.01 | Model | Implement Student + EMA Teacher | Teacher(t0)=Student(t0); no burn-in. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | teacher_initialization_test.json | PASS | Researcher
S4 | S4.02 | EMA | Implement MeanTeacherHook momentum=.001 | Teacher=.999 old + .001 Student. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | ema_timing_test.json | PASS | Researcher
S4 | S4.03 | EMA | skip_buffers=True | Frozen behavior. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | resolved SSL config | MATCH | Researcher
S4 | S4.04 | EMA | Update Teacher only after actual optimizer update | No EMA on microbatch. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | ema_timing_test.json | PASS | Researcher
S4 | S4.05 | AMP | AMP skipped step → EMA skip | Explicit test. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | amp_ema_skip_test.json | PASS | Researcher
S4 | S4.06 | Unlabeled weak | Weak view → Teacher | Resize + standard preprocessing + padding; no extra augmentation. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | ssl_augmentation_manifest.json | MATCH | Researcher
S4 | S4.07 | Unlabeled strong | Strong view → Student | brightness/contrast U(.90,1.10), grayscale R=G=B. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | ssl_augmentation_manifest.json | MATCH | Researcher
S4 | S4.08 | Geometry | Verify image–pseudo-box alignment | No coordinate mismatch. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | pseudo_bbox_alignment_report.json | PASS | Researcher
S4 | S4.09 | Pseudo | Lock pseudo thresholds | floor=.05, initial=.50, RPN=.90, RCNN cls=.90. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | resolved SSL config | MATCH | Researcher
S4 | S4.10 | Pseudo | Lock NMS/max | RPN .70/max1000; RCNN .50/max100. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | resolved SSL config | MATCH | Researcher
S4 | S4.11 | Regression | Regression reliability filtering | jitter=10, scale=.06, uncertainty<.02, min wh=.01/.01; no cls>.90 requirement. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | resolved SSL config | MATCH | Researcher
S4 | S4.12 | Loss | L_total=L_sup+4*L_unsup | No ramp-up/burn-in. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | preflight logs | MATCH | Researcher
S4 | S4.13 | Batch | L:U=1:1; B_L_eff=4; B_U_eff=4 | Paired labeled exposure must match SUP. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | training summary | MATCH | Researcher
S4 | S4.14 | Empty pseudo | Handle empty pseudo batch | No crash/fake supervision. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | empty_pseudo_batch_test.json | PASS | Researcher
S4 | S4.15 | Zero-GT | Verify SSL zero-GT handling | No Finding negatives valid. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | zero_gt_test.json | PASS | Researcher
S4 | S4.16 | Firewall | Verify hidden-U GT firewall | No hidden U GT in development/Q_pseudo. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | hidden_u_gt_firewall_report.json | PASS | Researcher
S4 | S4.17 | Resume | Restore Student+Teacher without resync | Restore optimizer/scheduler/scaler/update state. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | resume_equivalence_test.json | PASS | Researcher
S4 | S4.18 | Architecture | Preflight SSL R50 | Official path verified. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | ssl_r50_preflight.json | PASS | Researcher
S4 | S4.19 | Architecture | Preflight SSL Swin-T | Official path verified. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | ssl_swin_preflight.json | PASS | Researcher
S4 | S4.20 | Gate | Close S4 | All SSL paths + EMA/AMP/geometry/firewall verified. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | NOT_STARTED | S4 closure record | S4=CLOSED / PASS | Researcher
S5 | S5.01 | COCO | Implement bbox mAP@[.50:.95] | IoU .50:.05:.95; useCats=1; maxDets=100; no fixed score threshold before AP. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | coco_evaluator_golden_test.json | PASS | Researcher
S5 | S5.02 | COCO | Implement AP50/AP75/class-wise AP/AR | AR@[.50:.95], maxDets=100. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | coco_evaluator_golden_test.json | PASS | Researcher
S5 | S5.03 | Operating | Implement Recall@tau_eval=.50 | Category-aware one-to-one; IoU>=.50; native NMS/max100. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | operating_point_golden_test.json | PASS | Researcher
S5 | S5.04 | Operating | Implement FP/image | Same operating point. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | operating_point_golden_test.json | PASS | Researcher
S5 | S5.05 | Negative | Implement FP/negative + FAR | All detections on zero-GT are FP. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | operating_point_golden_test.json | PASS | Researcher
S5 | S5.06 | Q_pseudo | Implement PL-mAP@[.50:.95] | LAST EMA Teacher; fixed validation; accepted RCNN classification pseudo labels. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | qpseudo_path_golden_test.json | PASS | Researcher
S5 | S5.07 | Q_pseudo | Block BEST Teacher for Q_pseudo | BEST is official detection model only. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | qpseudo_path_golden_test.json | PASS | Researcher
S5 | S5.08 | Firewall | Verify no hidden-U/test GT in Q_pseudo | Validation only. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | qpseudo_path_golden_test.json | PASS | Researcher
S5 | S5.09 | Test Firewall | Keep test closed | No checkpoint/model/tuning/ablation selection using test. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | test_firewall_preflight.json | PASS | Researcher
S5 | S5.10 | Gate | Close S5 | Evaluator golden tests PASS. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | NOT_STARTED | S5 closure record | S5=CLOSED / PASS | Researcher
S6 | S6.01 | Stats | Implement mean/SD ddof=1 | Seed/run is inferential unit. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.02 | RQ2 | Implement one-sample t, alternative=greater | G_s, n=10, df=9, two-sided 95% CI. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.03 | RQ3 | Implement repeated-measures ANOVA + GG ALWAYS | Mauchly diagnostic only. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.04 | RQ3 | Implement six prespecified contrasts | 5-1,10-1,20-1,10-5,20-5,20-10. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.05 | RQ4 | Implement mixed model | Y~X+cell+(1¦seed), REML, Kenward–Roger. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.06 | RQ5 | Implement rare-class summaries | Atelectasis/Pneumothorax; NA not 0. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.07 | RQ6 | Implement two-sided t test | H_s on ΔFP/negative. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.08 | RQ7 | Implement two-sided architecture effect | D_s=A_Swin-A_R50. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.09 | Multiplicity | Implement Holm F2 m=4 | RQ3/RQ4/RQ6/RQ7. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | multiplicity_fixture_report.json | PASS | Researcher
S6 | S6.10 | Multiplicity | Implement Holm F3 m=6 | Six RQ3 contrasts. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | multiplicity_fixture_report.json | PASS | Researcher
S6 | S6.11 | Robustness | Implement exact sign-flip 2^10 | RQ2 one-sided; RQ6/RQ7 two-sided. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.12 | Robustness | Implement exactly 10 LOSO | Never exclude seed. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.13 | Sensitivity | Implement Friedman RQ3 | Sensitivity only. | IMPLEMENTATION_HANDOFF.md | MEDIUM | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.14 | Sensitivity | Implement CR2/Satterthwaite RQ4 | Cluster training_seed. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | statistical_fixture_report.json | PASS | Researcher
S6 | S6.15 | Provenance | Capture statistics environment + script hashes | Package/runtime/script identity. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | statistical_implementation_manifest.json | PASS | Researcher
S6 | S6.16 | Gate | Close S6 | All statistical fixtures PASS. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | NOT_STARTED | S6 closure record | S6=CLOSED / PASS | Researcher
S7 | S7.01 | Closure | PF01 — Data / membership / seed | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF01 | PASS | Researcher
S7 | S7.02 | Closure | PF02 — DataLoader / sampler / workers | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF02 | PASS | Researcher
S7 | S7.03 | Closure | PF03 — SUP R50 | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF03 | PASS | Researcher
S7 | S7.04 | Closure | PF04 — SUP Swin-T | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF04 | PASS | Researcher
S7 | S7.05 | Closure | PF05 — SSL R50 | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF05 | PASS | Researcher
S7 | S7.06 | Closure | PF06 — SSL Swin-T | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF06 | PASS | Researcher
S7 | S7.07 | Closure | PF07 — 1% scheduler | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF07 | PASS | Researcher
S7 | S7.08 | Closure | PF08 — 2064 scheduler + 100%-SUP evidence | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF08 | PASS | Researcher
S7 | S7.09 | Closure | PF09 — GT geometry | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF09 | PASS | Researcher
S7 | S7.10 | Closure | PF10 — pseudo geometry | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF10 | PASS | Researcher
S7 | S7.11 | Closure | PF11 — Teacher initialization | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF11 | PASS | Researcher
S7 | S7.12 | Closure | PF12 — EMA timing | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF12 | PASS | Researcher
S7 | S7.13 | Closure | PF13 — AMP skip → EMA skip | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF13 | PASS | Researcher
S7 | S7.14 | Closure | PF14 — empty pseudo | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF14 | PASS | Researcher
S7 | S7.15 | Closure | PF15 — zero-GT | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF15 | PASS | Researcher
S7 | S7.16 | Closure | PF16 — hidden-U firewall | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF16 | PASS | Researcher
S7 | S7.17 | Closure | PF17 — BEST/LAST | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF17 | PASS | Researcher
S7 | S7.18 | Closure | PF18 — Q_pseudo path | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF18 | PASS | Researcher
S7 | S7.19 | Closure | PF19 — COCO evaluator | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF19 | PASS | Researcher
S7 | S7.20 | Closure | PF20 — operating-point metrics | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF20 | PASS | Researcher
S7 | S7.21 | Closure | PF21 — resume path if enabled | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF21 | PASS | Researcher
S7 | S7.22 | Closure | PF22 — manifest/seed/provenance | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF22 | PASS | Researcher
S7 | S7.23 | Closure | PF23 — pilot-official isolation + test firewall | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF23 | PASS | Researcher
S7 | S7.24 | Closure | PF24 — frozen/hashable configs + pairing diff | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF24 | PASS | Researcher
S7 | S7.25 | Closure | PF25 — no unresolved protocol warning | Must PASS with direct evidence; no assumed/not-tested path. | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json#PF25 | PASS | Researcher
S7 | S7.26 | Gate | Generate GLOBAL_PREFLIGHT_REPORT.json | All closure groups PASS. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | GLOBAL_PREFLIGHT_REPORT.json | status=PASS | Researcher
S7 | S7.27 | Gate | Close S7 | No untested official path remains. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | NOT_STARTED | S7 closure record | S7=CLOSED / PASS | Researcher
S8 | S8.01 | Freeze | Freeze Git commit | Audited implementation commit immutable reference. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | frozen_source_manifest.json | PASS | Researcher
S8 | S8.02 | Freeze | Freeze Docker image + digest | Exact image identity captured. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | frozen_environment.json | PASS | Researcher
S8 | S8.03 | Freeze | Freeze source/contract hashes | Canonical hierarchy recorded. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | frozen_source_manifest.json | PASS | Researcher
S8 | S8.04 | Freeze | Freeze data membership hashes | Train/val/test/L/U locked. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | frozen_data_manifest.json | PASS | Researcher
S8 | S8.05 | Freeze | Freeze experiment configuration | FROZEN_EXPERIMENTAL_CONFIGURATION.yaml. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | FROZEN_EXPERIMENTAL_CONFIGURATION.yaml | PASS | Researcher
S8 | S8.06 | Freeze | Freeze evaluator | COCO/operating/Q_pseudo hashes. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | frozen_evaluator_manifest.json | PASS | Researcher
S8 | S8.07 | Freeze | Freeze statistics | Runtime/packages/scripts/hashes. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | frozen_statistics_manifest.json | PASS | Researcher
S8 | S8.08 | Firewall | Create TEST_FIREWALL_STATE.json | test_access_authorized=false before final-test gate. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | TEST_FIREWALL_STATE.json | PASS | Researcher
S8 | S8.09 | Authorization | Researcher review S7 evidence | No unresolved warning. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | review record | APPROVED | Researcher
S8 | S8.10 | Authorization | Create FREEZE_AUTHORIZATION.json | Researcher authorization before S9. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | FREEZE_AUTHORIZATION.json | YES | Researcher
S8 | S8.11 | Gate | Close S8 | Frozen manifests valid + authorization YES. | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | CRITICAL | NOT_STARTED | S8 closure record | S8=CLOSED / PASS | Researcher
S9 | S9.01 | Matrix | Prepare official run inventory | 80 SUP low-label +20 SUP100 +80 SSL =180. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | official_run_inventory.csv | 180 expected | Researcher
S9 | S9.02 | Guardrail | Enable pre_run_assertions | Verify source/config/data/seed/arch/method/budget/evaluator/firewall before launch. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | pre_run_assertions.json | PASS | Researcher
S9 | S9.03 | SUP | Execute 80 low-label SUP runs | 2 arch ×4 budgets ×10 seeds. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | official_training_summary.csv | 80/80 | Researcher
S9 | S9.04 | SUP Reference | Execute 20 100%-SUP runs | 2 arch ×10 seeds. | IMPLEMENTATION_HANDOFF.md | HIGH | NOT_STARTED | official_training_summary.csv | 20/20 | Researcher
S9 | S9.05 | SSL | Execute 80 low-label SSL runs | Paired seed/L_b/update exposure; EMA Teacher official model. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | official_training_summary.csv | 80/80 | Researcher
S9 | S9.06 | Retry | Technical retry uses same exact seed | Never retry valid poor result for performance. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | retry_deviation.json | Same seed | Researcher
S9 | S9.07 | Backup | Continuously sync logs/checkpoints | Vast active; Drive durable backup; verify checksum. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | backup_sync_manifest.json | PASS | Researcher
S9 | S9.08 | Checkpoint | Retain scientific checkpoints | SUP BEST/LAST; SSL BEST/LAST EMA Teacher. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | checkpoint_index.json | PASS | Researcher
S9 | S9.09 | Q_pseudo | Compute SSL Q_pseudo | LAST EMA Teacher on fixed validation. | IMPLEMENTATION_HANDOFF.md | CRITICAL | NOT_STARTED | qpseudo_validation.json | 80 complete | Researcher
S9 | S9.10 | Completeness | Verify 180 training runs closed | No replacement seed. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | completeness_report.json | 180/180 | Researcher
S9 | S9.11 | Ablation | Run locked OFAT validation-only campaign | R50 10%; 10 unique configs; 10 seeds/config; non-Main never test. | sn-article.tex / ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | results/ablation/* | 100 observations | Researcher
S9 | S9.12 | Final Test Gate | Prepare PRE_FINAL_TEST_GATE_REPORT | Only after training+ablation+frozen evaluator/stats. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | PRE_FINAL_TEST_GATE_REPORT.json | PASS | Researcher
S9 | S9.13 | Final Test Gate | Create eligible model inventory | 80 SUP +20 SUP100 +80 SSL BEST models. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | eligible_model_inventory.csv | 180 | Researcher
S9 | S9.14 | Final Test Gate | Researcher authorizes final test | Only after gate PASS. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | FINAL_TEST_AUTHORIZATION.json | YES | Researcher
S9 | S9.15 | Final Test | Evaluate 180 eligible models | No non-Main ablation test. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | CRITICAL | NOT_STARTED | official_final_test_results.csv | 180/180 | Researcher
S9 | S9.16 | Analysis | Generate paired effects + RQ1–RQ7 | Use locked statistical implementation. | ARTIFACT_AND_EVIDENCE_CONTRACT.md | HIGH | NOT_STARTED | analysis/rq1..rq7 | Complete | Researcher

## Stage_Status
Stage | Name | Stage Status | Progress % | PASS | Total Tasks | FAIL | BLOCKED | IN PROGRESS | Purpose | Gate to Next Stage | Dependency | Start Date | End Date | Owner | Notes
S0 | Source / Protocol Lock Verification | CLOSED / PASS | 100% | 14 | 14 | 0 | 0 | 0 | Verify canonical locked sources, hashes, Git baseline and governance manifests. | S0 governance artifacts valid + baseline commit/tag created | None |  |  | Researcher | S0 CLOSED / PASS. All 14 S0 tasks have evidence. Governance manifests validated; baseline commit=3635635beeff074534013eba5bd978ac34f9e1c9; PRE_IMPLEMENTATION_BASELINE resolves to the same commit.
S1 | Vast Runtime + Data Ingress + Storage/Backup | NOT_OPEN | 0% | 0 | 16 | 0 | 0 | 0 | Provision exact Vast runtime, transfer 4,894 JPG to Vast local/persistent storage, verify integrity and backup/restore foundation. | Runtime + 4,894 JPG + membership + storage/backup verification PASS | S0 = CLOSED / PASS |  |  | Researcher
S2 | Shared Infrastructure | NOT_OPEN | 0% | 0 | 16 | 0 | 0 | 0 | Implement shared dataset/loading/seeding/logging/checkpoint/guardrail infrastructure. | Shared infrastructure tests PASS | S1 = CLOSED / PASS |  |  | Researcher
S3 | Supervised Baseline | NOT_OPEN | 0% | 0 | 14 | 0 | 0 | 0 | Implement and preflight R50/Swin supervised paths and all scheduler/update branches. | All SUP official execution paths verified | S2 = CLOSED / PASS |  |  | Researcher
S4 | SSL Teacher–Student / EMA / Pseudo-label | NOT_OPEN | 0% | 0 | 20 | 0 | 0 | 0 | Implement and preflight Teacher/Student, EMA, pseudo-label, augmentation, hidden-U firewall and resume behavior. | All SSL paths + firewall + EMA/AMP/geometry PASS | S3 = CLOSED / PASS |  |  | Researcher
S5 | Evaluation + Q_pseudo | NOT_OPEN | 0% | 0 | 10 | 0 | 0 | 0 | Implement COCO evaluator, operating-point metrics and Q_pseudo path before test is opened. | Evaluator golden tests + validation/test firewall PASS | S4 = CLOSED / PASS |  |  | Researcher
S6 | Statistical Fixtures | NOT_OPEN | 0% | 0 | 16 | 0 | 0 | 0 | Implement statistical analysis functions and verify with synthetic/golden fixtures. | All statistical fixtures PASS | S5 = CLOSED / PASS |  |  | Researcher
S7 | Global Preflight | NOT_OPEN | 0% | 0 | 27 | 0 | 0 | 0 | Audit all official execution paths against closure criteria and artifact contract. | GLOBAL_PREFLIGHT_REPORT = PASS; no unresolved protocol-relevant warning | S6 = CLOSED / PASS |  |  | Researcher
S8 | Freeze + Researcher Authorization | NOT_OPEN | 0% | 0 | 11 | 0 | 0 | 0 | Freeze exact executable source/config/data/evaluator/statistics/environment and obtain researcher authorization. | Freeze manifests valid + RESEARCHER AUTHORIZATION = YES | S7 = CLOSED / PASS |  |  | Researcher
S9 | Official Training | NOT_AUTHORIZED | 0% | 0 | 16 | 0 | 0 | 0 | Execute official Main/reference matrix only after S8 PASS. | S8 PASS required before any official run | S8 = CLOSED / PASS |  |  | Researcher

## Evidence_Register
Evidence ID | Stage | Artifact / Evidence | Type | Required? | Status | Expected Path | Observed Path | SHA-256 / Identity | Verification | Source | Notes
E001 | S0 | Repository root | Artifact/Evidence | YES | VERIFIED | Repository root | D:\ssl_detection_xray_v2 | 4 canonical/operational filenames present | PASS | sn-article.tex / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E002 | S0 | a5f63ff018ee28a37ad2daa3fff337daf6b30faf34d9f12c6ff5c0fa92fe5237 | Artifact/Evidence | YES | VERIFIED | a5f63ff018ee28a37ad2daa3fff337daf6b30faf34d9f12c6ff5c0fa92fe5237 | sn-article.tex | a5f63ff018ee28a37ad2daa3fff337daf6b30faf34d9f12c6ff5c0fa92fe5237 | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E003 | S0 | d70e556d45f4a54a5e0498842b4932deef7991de0d986095ec85e546dcc2d026 | Artifact/Evidence | YES | VERIFIED | d70e556d45f4a54a5e0498842b4932deef7991de0d986095ec85e546dcc2d026 | IMPLEMENTATION_HANDOFF.md | d70e556d45f4a54a5e0498842b4932deef7991de0d986095ec85e546dcc2d026 | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E004 | S0 | 6f59fe4c097173fe0114763762dd191a6f3590caa57b28199b8bcf5100563639 | Artifact/Evidence | YES | VERIFIED | 6f59fe4c097173fe0114763762dd191a6f3590caa57b28199b8bcf5100563639 | ARTIFACT_AND_EVIDENCE_CONTRACT.md | 6f59fe4c097173fe0114763762dd191a6f3590caa57b28199b8bcf5100563639 | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E005 | S0 | Governance section | Artifact/Evidence | YES | VERIFIED | Governance section | sn-article.tex > IMPLEMENTATION_HANDOFF.md > ARTIFACT_AND_EVIDENCE_CONTRACT.md > workbook | SOURCE_HIERARCHY_LOCKED | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E006 | S0 | artifacts/governance/*.json | Governance validation | YES | VERIFIED | artifacts/governance/*.json | artifacts/governance/*.json | FAILED_COUNT=0; GOVERNANCE_VALIDATION=PASS | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md | Validate the four generated S0 governance JSON manifests before baseline closure.
E007 | S0 | artifacts/governance/scientific_source_manifest.json | Artifact/Evidence | YES | CREATED | artifacts/governance/scientific_source_manifest.json | artifacts/governance/scientific_source_manifest.json | schema_version=1.1; source hash verified | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E008 | S0 | artifacts/governance/implementation_contract_manifest.json | Artifact/Evidence | YES | CREATED | artifacts/governance/implementation_contract_manifest.json | artifacts/governance/implementation_contract_manifest.json | schema_version=1.1; implementation/source hashes verified | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E009 | S0 | artifacts/governance/artifact_contract_manifest.json | Artifact/Evidence | YES | CREATED | artifacts/governance/artifact_contract_manifest.json | artifacts/governance/artifact_contract_manifest.json | artifact_contract_version=1.1.0; schema_version=1.1; hierarchy/hashes verified | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E010 | S0 | artifacts/governance/schema_version.json | Artifact/Evidence | YES | CREATED | artifacts/governance/schema_version.json | artifacts/governance/schema_version.json | schema_version=1.1; artifact_contract_version=1.1.0 | PASS | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E011 | S0 | Git history | Artifact/Evidence | YES | CREATED | Git history | Git commit 3635635beeff074534013eba5bd978ac34f9e1c9 | 3635635beeff074534013eba5bd978ac34f9e1c9 | PASS | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E012 | S0 | Git tag PRE_IMPLEMENTATION_BASELINE | Artifact/Evidence | YES | CREATED | Git tag PRE_IMPLEMENTATION_BASELINE | PRE_IMPLEMENTATION_BASELINE | 3635635beeff074534013eba5bd978ac34f9e1c9 | PASS | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E013 | S0 | SOURCE_PROTOCOL_LOCK_REPORT.json | Artifact/Evidence | NO | NOT_APPLICABLE | SOURCE_PROTOCOL_LOCK_REPORT.json |  |  | NOT_APPLICABLE | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker | Not mandatory under the locked ARTIFACT_AND_EVIDENCE_CONTRACT. Retained only as a non-required historical tracker row; it must not gate S0 closure.
E014 | S1 | vast_environment.json | Artifact/Evidence | YES | NOT_CREATED | vast_environment.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E015 | S1 | docker_image_identity.json | Artifact/Evidence | YES | NOT_CREATED | docker_image_identity.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E016 | S1 | storage_environment.json | Artifact/Evidence | YES | NOT_CREATED | storage_environment.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E017 | S1 | dataset_transfer_manifest.json | Artifact/Evidence | YES | NOT_CREATED | dataset_transfer_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E018 | S1 | dataset_integrity_report.json | Artifact/Evidence | YES | NOT_CREATED | dataset_integrity_report.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E019 | S1 | split_membership_audit.json | Artifact/Evidence | YES | NOT_CREATED | split_membership_audit.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E020 | S1 | labeled_unlabeled_membership_audit.json | Artifact/Evidence | YES | NOT_CREATED | labeled_unlabeled_membership_audit.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E021 | S1 | class_mapping_audit.json | Artifact/Evidence | YES | NOT_CREATED | class_mapping_audit.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E022 | S1 | dataset_loader_manifest.json | Artifact/Evidence | YES | NOT_CREATED | dataset_loader_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E023 | S1 | backup_sync_manifest.json | Artifact/Evidence | YES | NOT_CREATED | backup_sync_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E024 | S1 | storage_restore_test.json | Artifact/Evidence | YES | NOT_CREATED | storage_restore_test.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E025 | S1 | S1 closure record | Artifact/Evidence | YES | NOT_CREATED | S1 closure record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E026 | S2 | dataset/DataLoader config | Artifact/Evidence | YES | NOT_CREATED | dataset/DataLoader config |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E027 | S2 | sample evidence | Artifact/Evidence | YES | NOT_CREATED | sample evidence |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E028 | S2 | zero_gt_test.json | Artifact/Evidence | YES | NOT_CREATED | zero_gt_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E029 | S2 | seed_propagation_audit.json | Artifact/Evidence | YES | NOT_CREATED | seed_propagation_audit.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E030 | S2 | dataloader_worker_seed_audit.json | Artifact/Evidence | YES | NOT_CREATED | dataloader_worker_seed_audit.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E031 | S2 | training_seed_invariance_audit.json | Artifact/Evidence | YES | NOT_CREATED | training_seed_invariance_audit.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E032 | S2 | preflight logs | Artifact/Evidence | YES | NOT_CREATED | preflight logs |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E033 | S2 | run_manifest.json | Artifact/Evidence | YES | NOT_CREATED | run_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E034 | S2 | sample logs | Artifact/Evidence | YES | NOT_CREATED | sample logs |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E035 | S2 | resume test | Artifact/Evidence | YES | NOT_CREATED | resume test |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E036 | S2 | guardrail tests | Artifact/Evidence | YES | NOT_CREATED | guardrail tests |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E037 | S2 | hidden_u_gt_firewall_report.json | Artifact/Evidence | YES | NOT_CREATED | hidden_u_gt_firewall_report.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E038 | S2 | S2 closure record | Artifact/Evidence | YES | NOT_CREATED | S2 closure record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E039 | S3 | sup_r50_preflight.json | Artifact/Evidence | YES | NOT_CREATED | sup_r50_preflight.json |  |  | PENDING | sn-article.tex / IMPLEMENTATION_HANDOFF.md
E040 | S3 | sup_swin_preflight.json | Artifact/Evidence | YES | NOT_CREATED | sup_swin_preflight.json |  |  | PENDING | sn-article.tex / IMPLEMENTATION_HANDOFF.md
E041 | S3 | resolved config | Artifact/Evidence | YES | NOT_CREATED | resolved config |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E042 | S3 | supervised_augmentation_manifest.json | Artifact/Evidence | YES | NOT_CREATED | supervised_augmentation_manifest.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E043 | S3 | training summary | Artifact/Evidence | YES | NOT_CREATED | training summary |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E044 | S3 | schedule_1pct_preflight.json | Artifact/Evidence | YES | NOT_CREATED | schedule_1pct_preflight.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E045 | S3 | schedule_2064_preflight.json | Artifact/Evidence | YES | NOT_CREATED | schedule_2064_preflight.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E046 | S3 | schedule_100pct_10284_preflight.json | Artifact/Evidence | YES | NOT_CREATED | schedule_100pct_10284_preflight.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E047 | S3 | validation history | Artifact/Evidence | YES | NOT_CREATED | validation history |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E048 | S3 | checkpoint evidence | Artifact/Evidence | YES | NOT_CREATED | checkpoint evidence |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E049 | S3 | resume_equivalence_test.json | Artifact/Evidence | YES | NOT_CREATED | resume_equivalence_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E050 | S3 | S3 closure record | Artifact/Evidence | YES | NOT_CREATED | S3 closure record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E051 | S4 | teacher_initialization_test.json | Artifact/Evidence | YES | NOT_CREATED | teacher_initialization_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E052 | S4 | ema_timing_test.json | Artifact/Evidence | YES | NOT_CREATED | ema_timing_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E053 | S4 | resolved SSL config | Artifact/Evidence | YES | NOT_CREATED | resolved SSL config |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E054 | S4 | amp_ema_skip_test.json | Artifact/Evidence | YES | NOT_CREATED | amp_ema_skip_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E055 | S4 | ssl_augmentation_manifest.json | Artifact/Evidence | YES | NOT_CREATED | ssl_augmentation_manifest.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E056 | S4 | pseudo_bbox_alignment_report.json | Artifact/Evidence | YES | NOT_CREATED | pseudo_bbox_alignment_report.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E057 | S4 | empty_pseudo_batch_test.json | Artifact/Evidence | YES | NOT_CREATED | empty_pseudo_batch_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E058 | S4 | ssl_r50_preflight.json | Artifact/Evidence | YES | NOT_CREATED | ssl_r50_preflight.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E059 | S4 | ssl_swin_preflight.json | Artifact/Evidence | YES | NOT_CREATED | ssl_swin_preflight.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E060 | S4 | S4 closure record | Artifact/Evidence | YES | NOT_CREATED | S4 closure record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E061 | S5 | coco_evaluator_golden_test.json | Artifact/Evidence | YES | NOT_CREATED | coco_evaluator_golden_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E062 | S5 | operating_point_golden_test.json | Artifact/Evidence | YES | NOT_CREATED | operating_point_golden_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E063 | S5 | qpseudo_path_golden_test.json | Artifact/Evidence | YES | NOT_CREATED | qpseudo_path_golden_test.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E064 | S5 | test_firewall_preflight.json | Artifact/Evidence | YES | NOT_CREATED | test_firewall_preflight.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E065 | S5 | S5 closure record | Artifact/Evidence | YES | NOT_CREATED | S5 closure record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E066 | S6 | statistical_fixture_report.json | Artifact/Evidence | YES | NOT_CREATED | statistical_fixture_report.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E067 | S6 | multiplicity_fixture_report.json | Artifact/Evidence | YES | NOT_CREATED | multiplicity_fixture_report.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E068 | S6 | statistical_implementation_manifest.json | Artifact/Evidence | YES | NOT_CREATED | statistical_implementation_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E069 | S6 | S6 closure record | Artifact/Evidence | YES | NOT_CREATED | S6 closure record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E070 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF01 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF01 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E071 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF02 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF02 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E072 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF03 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF03 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E073 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF04 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF04 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E074 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF05 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF05 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E075 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF06 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF06 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E076 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF07 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF07 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E077 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF08 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF08 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E078 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF09 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF09 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E079 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF10 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF10 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E080 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF11 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF11 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E081 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF12 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF12 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E082 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF13 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF13 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E083 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF14 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF14 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E084 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF15 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF15 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E085 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF16 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF16 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E086 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF17 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF17 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E087 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF18 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF18 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E088 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF19 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF19 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E089 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF20 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF20 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E090 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF21 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF21 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E091 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF22 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF22 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E092 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF23 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF23 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E093 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF24 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF24 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E094 | S7 | GLOBAL_PREFLIGHT_REPORT.json#PF25 | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json#PF25 |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E095 | S7 | GLOBAL_PREFLIGHT_REPORT.json | Artifact/Evidence | YES | NOT_CREATED | GLOBAL_PREFLIGHT_REPORT.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E096 | S7 | S7 closure record | Artifact/Evidence | YES | NOT_CREATED | S7 closure record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E097 | S8 | frozen_source_manifest.json | Artifact/Evidence | YES | NOT_CREATED | frozen_source_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E098 | S8 | frozen_environment.json | Artifact/Evidence | YES | NOT_CREATED | frozen_environment.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E099 | S8 | frozen_data_manifest.json | Artifact/Evidence | YES | NOT_CREATED | frozen_data_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E100 | S8 | FROZEN_EXPERIMENTAL_CONFIGURATION.yaml | Artifact/Evidence | YES | NOT_CREATED | FROZEN_EXPERIMENTAL_CONFIGURATION.yaml |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E101 | S8 | frozen_evaluator_manifest.json | Artifact/Evidence | YES | NOT_CREATED | frozen_evaluator_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E102 | S8 | frozen_statistics_manifest.json | Artifact/Evidence | YES | NOT_CREATED | frozen_statistics_manifest.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E103 | S8 | TEST_FIREWALL_STATE.json | Artifact/Evidence | YES | NOT_CREATED | TEST_FIREWALL_STATE.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E104 | S8 | review record | Artifact/Evidence | YES | NOT_CREATED | review record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E105 | S8 | FREEZE_AUTHORIZATION.json | Artifact/Evidence | YES | NOT_CREATED | FREEZE_AUTHORIZATION.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E106 | S8 | S8 closure record | Artifact/Evidence | YES | NOT_CREATED | S8 closure record |  |  | PENDING | IMPLEMENTATION_HANDOFF.md / Workbook operational tracker
E107 | S9 | official_run_inventory.csv | Artifact/Evidence | YES | NOT_CREATED | official_run_inventory.csv |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E108 | S9 | pre_run_assertions.json | Artifact/Evidence | YES | NOT_CREATED | pre_run_assertions.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E109 | S9 | official_training_summary.csv | Artifact/Evidence | YES | NOT_CREATED | official_training_summary.csv |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E110 | S9 | retry_deviation.json | Artifact/Evidence | YES | NOT_CREATED | retry_deviation.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E111 | S9 | checkpoint_index.json | Artifact/Evidence | YES | NOT_CREATED | checkpoint_index.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E112 | S9 | qpseudo_validation.json | Artifact/Evidence | YES | NOT_CREATED | qpseudo_validation.json |  |  | PENDING | IMPLEMENTATION_HANDOFF.md
E113 | S9 | completeness_report.json | Artifact/Evidence | YES | NOT_CREATED | completeness_report.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E114 | S9 | results/ablation/* | Artifact/Evidence | YES | NOT_CREATED | results/ablation/* |  |  | PENDING | sn-article.tex / ARTIFACT_AND_EVIDENCE_CONTRACT.md
E115 | S9 | PRE_FINAL_TEST_GATE_REPORT.json | Artifact/Evidence | YES | NOT_CREATED | PRE_FINAL_TEST_GATE_REPORT.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E116 | S9 | eligible_model_inventory.csv | Artifact/Evidence | YES | NOT_CREATED | eligible_model_inventory.csv |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E117 | S9 | FINAL_TEST_AUTHORIZATION.json | Artifact/Evidence | YES | NOT_CREATED | FINAL_TEST_AUTHORIZATION.json |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E118 | S9 | official_final_test_results.csv | Artifact/Evidence | YES | NOT_CREATED | official_final_test_results.csv |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md
E119 | S9 | analysis/rq1..rq7 | Artifact/Evidence | YES | NOT_CREATED | analysis/rq1..rq7 |  |  | PENDING | ARTIFACT_AND_EVIDENCE_CONTRACT.md

## Risks_Blockers
Risk ID | Stage | Date Raised | Category | Description | Severity | Probability | Status | Owner | Mitigation / Next Action | Evidence / Link | Resolved Date | Notes
R001 | S1 |  | Storage | Vast instance may be terminated before checkpoints/logs are durably backed up. | CRITICAL | MEDIUM | OPEN | Researcher | Implement verified continuous backup + restore test before model implementation. | backup_sync_manifest.json
R002 | S1 |  | Data | Training directly from Google Drive could cause unstable I/O and violate storage contract. | HIGH | LOW | OPEN | Researcher | Force DataLoader image root to Vast local/persistent storage. | dataset_loader_manifest.json
R003 | S4 |  | Scientific | Hidden U ground truth could leak via dataset/evaluator hooks. | CRITICAL | LOW | OPEN | Researcher | Hard firewall test before official SSL path. | hidden_u_gt_firewall_report.json
R004 | S9 |  | Recovery | Technical interruption could lose optimizer/Teacher/AMP state. | HIGH | MEDIUM | OPEN | Researcher | Verify latest_resume and same-seed resume path before S8. | resume_equivalence_test.json

## S9_Official_Matrix
Run ID | Condition Role | Method | Architecture | Budget | Seed Index | Training Seed | Expected | Training Status | Attempt Used | BEST Checkpoint | LAST Checkpoint | Q_pseudo Status | Backup Verified | Eligible Final Test | Final Eval Status | Notes
OFF_SUP_R50_B01_S01 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S02 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S03 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S04 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S05 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S06 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S07 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S08 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S09 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B01_S10 | MAIN_LOW_LABEL | SUP | R50-FPN | B01 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S01 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S02 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S03 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S04 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S05 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S06 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S07 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S08 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S09 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B05_S10 | MAIN_LOW_LABEL | SUP | R50-FPN | B05 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S01 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S02 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S03 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S04 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S05 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S06 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S07 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S08 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S09 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B10_S10 | MAIN_LOW_LABEL | SUP | R50-FPN | B10 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S01 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S02 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S03 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S04 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S05 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S06 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S07 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S08 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S09 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B20_S10 | MAIN_LOW_LABEL | SUP | R50-FPN | B20 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S01 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S02 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S03 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S04 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S05 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S06 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S07 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S08 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S09 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B01_S10 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B01 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S01 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S02 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S03 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S04 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S05 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S06 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S07 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S08 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S09 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B05_S10 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B05 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S01 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S02 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S03 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S04 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S05 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S06 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S07 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S08 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S09 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B10_S10 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B10 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S01 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S02 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S03 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S04 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S05 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S06 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S07 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S08 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S09 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B20_S10 | MAIN_LOW_LABEL | SUP | Swin-T-FPN | B20 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S01 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S02 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S03 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S04 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S05 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S06 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S07 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S08 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S09 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B01_S10 | MAIN_LOW_LABEL | SSL | R50-FPN | B01 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S01 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S02 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S03 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S04 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S05 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S06 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S07 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S08 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S09 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B05_S10 | MAIN_LOW_LABEL | SSL | R50-FPN | B05 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S01 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S02 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S03 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S04 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S05 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S06 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S07 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S08 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S09 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B10_S10 | MAIN_LOW_LABEL | SSL | R50-FPN | B10 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S01 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S02 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S03 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S04 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S05 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S06 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S07 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S08 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S09 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_R50_B20_S10 | MAIN_LOW_LABEL | SSL | R50-FPN | B20 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S01 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S02 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S03 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S04 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S05 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S06 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S07 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S08 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S09 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B01_S10 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B01 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S01 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S02 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S03 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S04 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S05 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S06 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S07 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S08 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S09 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B05_S10 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B05 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S01 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S02 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S03 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S04 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S05 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S06 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S07 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S08 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S09 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B10_S10 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B10 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S01 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S02 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S03 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S04 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S05 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S06 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S07 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S08 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S09 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SSL_SWIN_B20_S10 | MAIN_LOW_LABEL | SSL | Swin-T-FPN | B20 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | PENDING | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S01 | SUP_REFERENCE | SUP | R50-FPN | B100 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S02 | SUP_REFERENCE | SUP | R50-FPN | B100 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S03 | SUP_REFERENCE | SUP | R50-FPN | B100 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S04 | SUP_REFERENCE | SUP | R50-FPN | B100 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S05 | SUP_REFERENCE | SUP | R50-FPN | B100 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S06 | SUP_REFERENCE | SUP | R50-FPN | B100 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S07 | SUP_REFERENCE | SUP | R50-FPN | B100 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S08 | SUP_REFERENCE | SUP | R50-FPN | B100 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S09 | SUP_REFERENCE | SUP | R50-FPN | B100 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_R50_B100_S10 | SUP_REFERENCE | SUP | R50-FPN | B100 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S01 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 1 | 204886845 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S02 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 2 | 1480646854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S03 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 3 | 1798418854 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S04 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 4 | 2045683682 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S05 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 5 | 1814859839 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S06 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 6 | 1603952859 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S07 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 7 | 1878351743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S08 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 8 | 875651179 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S09 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 9 | 477581743 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED
OFF_SUP_SWIN_B100_S10 | SUP_REFERENCE | SUP | Swin-T-FPN | B100 | 10 | 869675675 | YES | NOT_STARTED |  |  |  | NOT_APPLICABLE | NO | NO | NOT_AUTHORIZED

## Reference_Locks
LOCKED REFERENCES & SCIENTIFIC CONSTANTS
Priority | File | Role | SHA-256 | State | Rule
Priority 1 | sn-article.tex | Scientific source of truth | a5f63ff018ee28a37ad2daa3fff337daf6b30faf34d9f12c6ff5c0fa92fe5237 | LOCKED | Methodology wins
Priority 2 | IMPLEMENTATION_HANDOFF.md | Implementation contract | d70e556d45f4a54a5e0498842b4932deef7991de0d986095ec85e546dcc2d026 | LOCKED | No scientific drift
Priority 3 | ARTIFACT_AND_EVIDENCE_CONTRACT.md | Artifact/evidence contract | 6f59fe4c097173fe0114763762dd191a6f3590caa57b28199b8bcf5100563639 | LOCKED | Artifact contract v1.1.0
Operational | SSOD_S0_S9_Implementation_Management_Dashboard.xlsx | S0–S9 execution tracker / project control |  | LIVE TRACKER | Operational only; not part of the locked contract hierarchy
Locked Item | Value | Unit/Role | Notes
Dataset images | 4894 | images | Controlled working scope
Train / Val / Test | 3426 / 734 / 734 | images | Fixed membership
No Finding train/val/test | 350 / 75 / 75 | images | Zero-GT; not class 15
Detection classes | 14 | classes | Abnormality classes
partition_seed | 42 | integer | No seed search
Training seeds | 10 | seeds | Same ordered list SUP/SSL
Official main/reference runs | 180 | runs | 80 SUP low-label + 20 SUP100 + 80 SSL
Validation interval | 172 | actual optimizer updates | All official training
Standard updates | 2064 | updates | 5/10/20%
1% updates | 1032 | updates | Proportional schedule
100%-SUP updates | 10284 | updates | Reference path
SSL EMA momentum | 0.001 | MeanTeacherHook momentum | Teacher=.999 old+.001 Student
SSL L:U | 1:1 | ratio | B_L_eff=4; B_U_eff=4
SSL unsup weight | 4 | lambda_u | No ramp/burn-in
Q_pseudo | PL-mAP@[.50:.95] | validation | LAST EMA Teacher

## Source_Map
Source | Role | Priority | Workbook Usage | State | Notes
sn-article.tex | Scientific methodology | 1 | Scientific behavior, evaluation, statistics, ablation, locked values | LOCKED | Canonical scientific source
IMPLEMENTATION_HANDOFF.md | Implementation contract | 2 | Execution requirements, preflight closure, prohibited behaviors, official matrix | LOCKED | Operational seed list included
ARTIFACT_AND_EVIDENCE_CONTRACT.md | Artifact/evidence contract | 3 | Evidence paths, manifests, backup, final-test gate, provenance | LOCKED | v1.1.0
SSOD_S0_S9_Implementation_Management_Dashboard.xlsx | Operational execution tracker | Non-contract | Stage status, detailed tasks, evidence register, risks/blockers, S9 run matrix and dashboard | LIVE TRACKER | The only S0–S9 execution tracker; does not override the three locked canonical documents